## Salesforce - Roche
Jira Ticket | Status | Assigned To | Category | Type | Description | Sprint ¦ Release | CM LOE | ENG LOE | ROM | Research Hours | Comments
RVSC-47 | Not Started | Eng | People Finder | Improvement | Hide or remove system users appearing in People Finder view |  |  |  | Complex > 41 hours |  | Pending SSO - Displaying all users part of salesforce - one way to show only part of community, are profiles enabled within the community - all salesforce or community users
RVSC-49 | Not Started | Eng | People Finder | Improvement | Add Search by Name |  |  |  | Medium 9 - 20 hours |  | Pending SSO - Text field or drop down
RVSC-50 | Not Started | Eng | People Finder | Improvement | Linking to LinkedIn and/or Roche Profile |  |  |  | Medium 9 - 20 hours |  | Pending SSO
RVSC-52 | Not Started | Eng | Meet the Team | New Feature | Clickable map; country profile type of page |  |  |  | Complex > 41 hours |  | Pending SSO
RVSC-56 | In Progress | Eng/CM | Platform | Task | Question with no best answer filter |  |  |  | Complex > 41 hours | 2 | OOTB - it will have to be custom component for expected behavior
RVSC-62 | In Progress | CM | Platform | Task | Recently Answered Questions Name Change | SR1 11-1 to 11-12 | 1 |  | Low < 8 hours |  | CM can make the change in Rich Content Editor within Builder
RVSC-59 | In Progress | Eng/CM | Platform | Improvement | Unanswered Questions Widget |  |  |  | Complex > 41 hours | 2 | OOTB - it will have to be custom component for expected behavior
RVSC-45 | In Progress | Eng | Carousel | Improvement | Open image links in a new tab: Carousel checkbox: - Internal community links (within Viewics community): Open in same window - External community links: open in a new tab | SR1 11-1 to 11-12 |  | 16 | Medium 9 - 20 hours
RVSC-46 | In Progress | Eng/CM | Articles | Improvement | Enable comments | SR1 11-1 to 11-12 | 1 | 2 | Low < 8 hours |  | Done in stage ¦ CM can move to production
RVSC-48 | In Progress | Eng/CM | Carousel | Improvement | - Header Title - "Hot News/Hot topics" | SR1 11-1 to 11-12 |  | 4 | Low < 8 hours |  | Done in Stage
RVSC-51 | In Progress | Eng | Platform | Improvement | New member notifications | SR1 11-1 to 11-12 |  | 24 | High 21 - 40 hours
RVSC-61 | In Progress | CM | Platform | Task | Reports ¦ New User Report | SR1 11-1 to 11-12 | 1 |  | Low < 8 hours |  | New Member Report has been created in stage
RVSC-54 | In Progress | CM | Platform | Task | Analytics - Community/User | SR1 11-1 to 11-12 | 16 |  | Medium 9 - 20 hours
RVSC-55 | In Progress |  | Platform | New Feature | SSO Integration
RVSC-60 | Complete | Eng | Platform | Task | SFDC Expired Certificate Notification | SR1 11-1 to 11-12 |  | 2 | Low < 8 hours
RVSC-53 | Complete | Eng/CM | Platform | Bug | Log out - Viewics Connect - Favicon | SR1 11-1 to 11-12 | 0.5 | 2 | Low < 8 hours
RVSC-57 | Complete | Eng | Platform | Improvement | Self-Registration ¦ Add Roles to the Drop-down | SR1 11-1 to 11-12 |  | 1 | Low < 8 hours
RVSC-58 | Complete | Eng | People Finder | Improvement | Add roles | SR1 11-1 to 11-12 |  | 1 | Low < 8 hours
[5 empty] | 52 | Eng Hours | 18.5 | 52
[5 empty] | 19.5 | CM Hours
[5 empty] | 6.5 | SR1 Completed